# PhD Research Plan — Physics-Informed Mamba Digital Twin for Mecanum-Wheeled Omnidirectional Robots

Candidate: Vishvesh Koranne
Guide: Prof. Shital S. Chiddarwar
Institute: VNIT Nagpur, Department of Mechanical Engineering
Target: PhD Thesis + 2 journal papers
Date: 2026-07-17

———————————————————————————————————————————

# AIM

To develop a resilient, data-driven control architecture for 4WD Mecanum-Wheeled Omnidirectional Robots (FMWOR) for dynamic real-world conditions.

# GOAL

Design and deploy a Physics-Informed Mamba State-Space-Model Neural Network based Digital Twin architecture for real-time FMWOR control, robust to nonlinear frictional interaction, unmodeled slipping, and mechanical wear of mecanum wheel rollers.

# OBJECTIVES

| Obj | Description | Success Metric |
| --- | --- | --- |
| O1 | High-fidelity Data Generation: model slippage with lumped roller spin model for sim-to-real pipeline — Julia LuGre-Adamov friction ODE → holistic excitation dataset → MuJoCo cross-validation → custom 4WD platform sim | • MuJoCo state RMSE ≤ 5% vs Julia on high-amplitude excitation trajectories • Custom sim calibrated to hardware ≤ 5% parameter error |
| O2 | Mamba + PINN architecture for Digital Twin — selective SSM backbone + frictional force-based physics loss — per-wheel (μ, χ) heads for forward + >Δ(state) based inverse force reconstruction | • ≤ 1 ms inference for controller processing • Forward dynamics RMSE ≤ 5% envelope • μ RMSE ≤ 0.05, χ RMSE ≤ 0.001 (whitelisted) • ≤ 10ms lag between DT and physical robot |
| O3 | Hardware validation — zero-shot (floor μ variation) → one-shot and few-shot (payload/CoM variation) → online ID (roller wear) on custom 4WD | • Phase 1: pose RMSE ≤ 2× sim (μ ∈ [0.3, 0.8]) • Phase 2: pose RMSE ≤ 3× sim (±100% payload, ±20% CoM) • Phase 3: μ(t) tracking R² ≥ 0.8 vs wear progression |
| O4 | Certifiability-by-design framework — output-bounded PINN + reachability + runtime monitor for SIL 1–2 evidence | • Lipschitz-constrained Mamba blocks (spectral norm ≤ 1) • Runtime monitor FP ≤ 1% • Reachable-set over-approx ≤ 2× true envelope |

# IN-SCOPE

| Item | Reason |
| --- | --- |
| Slightly uneven terrain | Should be deployable on road-like roughness, beam rivet bump dockyards |
| Inclined terrain | Inclination upto x degrees |
| µ above 0.3 for traction | Keep the operating range wide enough |
| Roller wear monitoring for wheels | Keeps the forward dynamics force reconstruction for MPC viable |
| Mid trajectory CoM shift (±100% payload, ±10% CoM position wrt body length) | Keeps the operation viable for dynamic real-world-like conditions |

# OUT-OF-SCOPE (Explicit Boundaries)

| Item | Reason |
| --- | --- |
| Full PL d / SIL 2 certification | Requires Category 3 hardware, safety PLC, FSA — platform-level, not learned-component |
| Hardware fault injection (IEC 61508-2) | Requires safety-rated test lab, fault injectors, months campaign — validates platform, not PINN architecture |
| Multi-robot coordination | Single-platform focus |
| End-to-end RL/IL policy | Model-based architecture (policy-based MPC/SMC) |
| Battery/energy as primary objective | Byproduct of slip reduction |

# TASK HIERARCHY (Non-Linear Time, with Risk Forks)

## O1: SIM-TO-REAL PIPELINE

### T1.1 Julia ODE refinement & dataset generation (COMPLETE)

39-D stiff ODE (FBDF2, reltol 1e-9, 2 kHz)

24 excitation profiles, μ ∈ {0.3, 0.5, 0.8}, χ ∈ [0, 0.008]

Output: Arrow (5345/5670 whitelisted)

### Deliverable: Dataset with physics and down-sampling-consistentency analytics

### T1.2 MuJoCo cross-validation (youBot) [PARALLEL with T2.1]

Replicate geometry + LuGre in MJCF

Pass/Fail: State RMSE ≤ 5% AND Slip RMSE ≤ 8%

#### 🍴 FORK: MuJoCo–Julia mismatch >5% [Risk R2]

F1.2a: Debug contact model (roller handoff, Hertz params)

F1.2b: If unresolved → Use Julia data ONLY for PINN training

F1.2c: Restrict MuJoCo to custom platform sys-ID only

### Deliverable: Cross-validation report with pass/fail decision

### T1.3 Custom 4WD platform system identification [DEPENDS ON HARDWARE]

MuJoCo model → hardware parameter fitting (mass, inertia, friction)

Target: ≤ 5% parameter error vs physical measurements

#### 🍴 FORK: Custom platform hardware delays [Risk R3]

F1.3a: Parallel sim work continues (Julia + MuJoCo)

F1.3b: Hardware-in-loop with recorded Julia data

F1.3c: Defer hardware-dependent tasks; advance O2/O4

### Deliverable: Calibrated MuJoCo model for custom platform

## O2: MAMBA-PINN ARCHITECTURE [STARTS AFTER T1.1, PARALLEL WITH T1.2/T1.3]

### T2.1 Architecture design & implementation [CURRENT TESTING IN THIS PHASE]

### T2.2 Physics-informed training (3 stages) [NEEDS T1.2 PASS/FAIL DECISION]

Stage 1 Grounding→Phys Model Training: λ_phys ramped up to 1, supervised on 5345 whitelisted

Stage 2 Physics: λ_phys=1.0, force-based physics loss for model learning on whitelisted trajectories

Stage 3 Online Identification

Targets: dyn RMSE ≤ 5%, μ RMSE ≤ 0.05, χ RMSE ≤ 0.001

### T2.3 Inference optimization & profiling [NEEDS T2.2 MODEL]

Target: ≤ 1 ms

#### 🍴 FORK: Mamba inference >1 ms [Risk R1]

F2.3: Fallback target: ~0.35 ms with increased params

### Deliverable: ONNX/TensorRT model + latency report

## O3: HARDWARE VALIDATION [STARTS AFTER T2.3 MODEL READY + T1.3 CALIBRATED]

### T3.1 Phase 1 — Floor μ variation (zero-shot)

Surfaces: epoxy (0.3), concrete (0.5), carpet (0.6), steel (0.3)

Trajectories: octagon, coupled_vω, spiral_iso × 3 reps

Metrics: pose RMSE (% traj length) ≤ 2× sim; μ RMSE ≤ 0.05

Control: MPC (horizon=20, 1 kHz) using twin + ASMC fallback

### T3.2 Phase 2 — Payload/CoM shift/Inclination (one-shot to few-shot)

Payload: +5.5% (1 kg), +11% (2 kg); CoM offset: ±20% l, gradient variation up to x degrees

Trajectories: square, ellipse, figure8 × 2 reps

Adaptation: 5 trajectories → fine-tune μ heads

Metrics: pose RMSE ≤ 3× sim; μ drift ≤ 0.03 vs baseline

### T3.3 Phase 3 — Roller wear (online ID)

Wear stages: 0% → 25% → 50% → 75% → 100% (sandpaper abrasion)

Trajectories: spin_creep, multisine50 × 2 reps (spin-rich)

Primary: μ(t) tracking R² ≥ 0.8 vs measured progression

Secondary: χ(t) correlation with μ(t) (optional, wear mechanism)

Exploratory: Motor current FFT at 12× wheel freq → wear index

Metrics: pose RMSE growth ≤ 2× per stage

### Deliverable: Hardware validation report + sim-to-real gap characterization

## O4: CERTIFIABILITY FRAMEWORK [INFORMED BY O4 RESULTS]

### T4.1 Lipschitz-constrained Mamba blocks [USES O3 MEASURED GAPS]

Spectral normalization on Mamba projections (spectral norm ≤ 1)

Compute Lipschitz constants per layer (power iteration)

Calibrate κ in monitor using O4 Phase 1–2 disturbance statistics

Output bounding proof for 20-step horizon

### T4.2 Reachability analysis [VALIDATED ON O3 TRAJECTORIES]

Zonotope propagation through PINN

Target: reachable-set over-approximation ≤ 2× true envelope

Validation: Monte Carlo on O4 hardware data vs analytical bounds

Adjust horizon/partitioning based on O4 chatter frequencies

### T4.3 Runtime monitor design & validation [DEPLOYED ON O3 HARDWARE]

Monitor: ||x_meas - x_pred|| > κ·σ → safe stop trigger

κ calibrated from O4 Phase 1–2 residual distributions

False positive target: ≤ 1% (measured on O4 nominal runs)

Fault injection: bit-flip, NaN, OOD input → detection rate

#### 🍴 FORK: Certifiability evidence insufficient [Risk R5]

F3.3a: Scope claim: "enables SIL 1–2 evidence for learned component"

F3.3b: Explicitly exclude: full PL d, Category 3 hw, FSA

F3.3c: Produce: architecture diagram, bounds report, monitor FP rate

### Deliverable: Certifiability evidence package (Lipschitz + reachability + monitor) validated on hardware

# TIMING INDEPENDENCE MAP

| Task | Can Start | Blocks | Parallel With |
| --- | --- | --- | --- |
| T1.1 | Day 0 | T1.2, T2.1 | — |
| T1.2 | T1.1 done | T2.2 (data decision) | T2.1 |
| T2.1 | T1.1 done | T2.2 | T1.2, T1.3 |
| T1.3 | Hardware ready | T3.1 (calibrated sim) | T2.1, T2.2 |
| T2.2 | T1.2 decision + T2.1 | T2.3 | T1.3 |
| T2.3 | T2.2 done | T3.1 (model) | — |
| T3.1 | T2.3 + T1.3 | T3.2, T4.1 (gap data) | — |
| T3.2 | T3.1 | T3.3, T4.1/4.2 | — |
| T3.3 | T3.2 | T4.2/4.3 (validation) | — |
| T4.1 | T4.1 (initial gaps) | T4.2, T4.3 | T3.2, T3.3 |
| T4.2 | T4.1 + T3.2 data | T4.3 | T3.3 |
| T4.3 | T4.1 + T3.3 data | — | — |

Critical path: T1.1 → T1.2 → T2.2 → T2.3 → T3.1 → T3.2 → T3.3 → T4.3

Parallel tracks: T2.1 runs during T1.2/T1.3; T4.1 starts early with T3.1 data and refines through T3.3

# RISK REGISTRY (Mapped to Task Forks)

| Risk ID | Risk | Likelihood | Impact | Primary Fork Location |
| --- | --- | --- | --- | --- |
| R1 | Mamba inference >1 ms on Orin | Medium | High | O2 → T2.3 🍴 |
| R2 | MuJoCo–Julia mismatch >5% | Low | Medium | O1 → T1.2 🍴 |
| R3 | Custom platform hardware delays | Medium | High | O1 → T1.3 🍴 |
| R5 | Certifiability evidence insufficient | Low | Medium | O3 → T3.3 🍴 |